DECISION BRIEF FOR THE INCIDENT MANAGER

Where to deploy 24 hours of mop-up capacity

March 2026 Supplementary Immunization Activity | Bansara State
Prepared by the GIS & Data Analytics Unit, August 2026

THE DECISION

Target Wards: Idi-Oro, Gwarin, Katsuma, Ilela
Send all available teams to the ten identified clusters first — nine are in Idi-Oro, one in Kungomi ward, Katsuma. That absorbs 18 of your 32 team-days. Spend the remaining 14 in Bayoyi, Famade, Okradu, Baluru and Ekduru wards.

Impact: This reaches an estimated 28,368 children — 68% of all children with no vaccination record from any source.

THE SITUATION IN FOUR NUMBERS

| 170,404 doses reported by teams | 31% of visits confirmed by GPS tracking | 446 settlements with no record from any source | 41,868 children in those settlements |
| --- | --- | --- | --- |

DEPLOYMENT PLAN (32 TEAM-DAYS)

| Priority | Where | Team-days | Children |
| --- | --- | --- | --- |
| 1 | Umyosa & Baluru clusters (Idi-Oro) | 5 | 8,742 |
| 2 | Okradu, Bayoyi, Satita (Idi-Oro) | 3 | 3,023 |
| 3 | Baluru C7, Ekngoyi C8/C9 (Idi-Oro) | 3 | 2,207 |
| 4 | Kungomi ward (Katsuma) 54 settlements | 7 | 4,849 |
| 5 | Residual: Bayoyi, Famade, Okradu, Baluru, Ekduru wards (Idi-Oro) | 14 | 9,547 |
| TOTAL |  | 32 | 28,368 |

Planning basis: 8 settlements per team per day, taken from the working stops actually observed in this round rather than from a microplan assumption.

THREE THINGS THAT NEED YOUR DECISION TODAY

Reported coverage cannot be verified for 1,260 settlements. Eight teams reported settlements 19–66 km from where their trackers place them, on devices that worked normally all five days. Seven reported 'settlements' do not exist in the masterlist at all. This is as consistent with a data-entry or keying fault as missing — do not sanction teams on this evidence.

Team T25 worked five full days in Ilela and filed no tally at all. Thirty settlements there show GPS evidence of a visit but no reported doses. Recover that book before the final coverage figure is signed off.

Five 'inaccessible' settlements have doses reported against them. These were classified inaccessible on security grounds before the round. Either the security classification is out of date or the reports are misattributed. Reconcile with your security lead before the next round is planned.

WHAT THIS BRIEF DOES NOT TELL YOU

The clusters are areas, not lists of children. They do not identify which individual settlement was missed, and they say nothing about whether any particular child was vaccinated. A settlement inside a cluster may have been fully reached; one outside may have been missed.

GPS evidence is also weaker in dense urban Idi-Oro, where positional accuracy averages 34 m against 8 m in rural wards, so treat the Idi-Oro figures as the better-supported direction of travel, not as a precise count.

WHERE THE 41,868 UNREACHED CHILDREN ARE — TOP NINE WARDS

Legend: Green = Reached by the 24-hour plan above. Grey = Not reached: carry into the next round.

| Ward (LGA) | Unreached Children | Status in 24-Hr Plan | Action |
| --- | --- | --- | --- |
| Umyosa (Idi-Oro) | 5,000 | Reached | Targeted in 24-hr plan |
| Baluru (Idi-Oro) | 4,937 | Reached | Targeted in 24-hr plan |
| Satita (Idi-Oro) | 4,857 | Not Reached | Carry into next round |
| Bayoyi (Idi-Oro) | 3,274 | Reached | Targeted in 24-hr plan |
| Okradu (Idi-Oro) | 3,174 | Reached | Targeted in 24-hr plan |
| Bishama (Idi-Oro) | 2,746 | Reached | Targeted in 24-hr plan |
| Ekngoyi (Idi-Oro) | 2,525 | Not Reached | Carry into next round |
| Famade (Idi-Oro) | 2,189 | Reached | Targeted in 24-hr plan |
| Ekduru (Idi-Oro) | 1,519 | Reached | Targeted in 24-hr plan |